## User Stories
Story ID | Use Case | Actor | User Story | Acceptance Criteria | Priority | Story Points | Target Date
US-01 | UC-01 Register Account | Employee/User | As a new user, I want to register with my name, email, and password so that I can access SmartDesk. | Duplicate emails rejected; password securely hashed; success confirmation returned. | Must | 2 | 2026-09-03
US-02 | UC-02 Login | Employee/Agent/Admin | As a registered user, I want to log in so that I receive an authenticated session and land on my role's dashboard. | Valid credentials return a token; invalid credentials return a controlled error; role determines redirect. | Must | 2 | 2026-09-04
US-03 | Authorization (FR 5.1) | System | As the system, I want to enforce role-based authorization so that users only access permitted actions. | Protected endpoints reject unauthenticated/unauthorized requests; roles checked server-side. | Must | 3 | 2026-09-04
US-04 | UC-03 Create Ticket | Employee | As an employee, I want to create a ticket with a title and description so IT can help me. | Ticket saved with status OPEN; validation errors block bad input; AI analysis triggered when enabled. | Must | 3 | 2026-09-07
US-05 | UC-04 View Own Tickets | Employee | As an employee, I want to view my own tickets so I can track their progress. | List shows only the employee's tickets with status/priority/category/dates; empty state when none exist. | Must | 2 | 2026-09-09
US-06 | UC-05 View Ticket Details | Employee/Agent/Admin | As an authorized user, I want to view full ticket details so I understand its current state. | Shows metadata, comments, assignment, status, and AI info where available; unauthorized users get an error. | Must | 2 | 2026-09-08
US-07 | UC-07 Assign Ticket | IT Agent | As an IT agent, I want to assign a ticket to myself or another agent so ownership is clear. | Only authorized assignees accepted; ticket appears in assignee's workload. | Must | 2 | 2026-09-08
US-08 | UC-08 Update Ticket Status | IT Agent | As an IT agent, I want to update ticket status and priority so the ticket reflects its real progress. | Status limited to OPEN/IN_PROGRESS/RESOLVED; invalid transitions rejected; update timestamp recorded. | Must | 2 | 2026-09-08
US-09 | UC-09 Add Ticket Comment | Employee/IT Agent | As a ticket participant, I want to add comments so I can communicate updates. | Comments store author/timestamp/content; shown chronologically; empty comments rejected. | Must | 2 | 2026-09-11
US-10 | UC-10 Resolve Ticket | IT Agent | As an IT agent, I want to resolve a ticket so the employee knows their issue is fixed. | Status set to RESOLVED; resolution timestamp recorded; employee can see resolved state. | Must | 2 | 2026-09-08
US-11 | UC-06 Analyze Ticket with AI | System/IT Agent | As the system, I want to send a new ticket's description to the AI service so it gets classified automatically. | AI returns category, priority, summary, suggested actions; malformed/failed AI responses don't block ticket creation. | Must | 3 | 2026-09-14
US-12 | UC-06 Analyze Ticket with AI (review) | IT Agent | As an IT agent, I want to review AI suggestions on a ticket before acting on them. | AI analysis displayed on ticket details; agent can proceed with or override the suggestion. | Should | 2 | 2026-09-14
US-13 | UC-11 View Dashboard Statistics | IT Agent/Admin | As an IT agent or admin, I want to see ticket statistics so I can monitor service-desk activity. | Dashboard shows counts by status, category, and priority; empty/zero states handled gracefully. | Must | 3 | 2026-09-15
US-14 | UC-11 View Dashboard Statistics (workload) | Admin | As an admin, I want to see agent workload so I can balance ticket assignment. | Dashboard lists agents with open/assigned ticket counts. | Should | 2 | 2026-09-15
US-15 | UC-12 Manage Users | Admin | As an admin, I want to view and manage user accounts so I can maintain the system. | Admin-only access; permitted attributes/role changes validated and saved. | Should | 2 | 2026-09-15
US-16 | UC-13 Manage Categories | Admin | As an admin, I want to create and edit ticket categories so tickets stay well organized. | Duplicate/invalid categories rejected; new category becomes available for tickets. | Should | 2 | 2026-09-15
US-17 | API Documentation (NFR) | Developer | As a developer, I want Swagger/OpenAPI docs so the frontend can integrate against a clear contract. | Swagger UI lists all endpoints with request/response schemas. | Should | 2 | 2026-09-15
US-18 | Testability (NFR) | Developer | As a developer, I want automated backend tests so core logic is protected against regressions. | JUnit/Mockito cover auth, ticket, and AI services; Postman collection covers main endpoints. | Should | 3 | 2026-09-16
US-19 | Deployability - Docker (NFR) | Developer | As a developer, I want the app containerized so it runs consistently across environments. | Dockerfiles for frontend/backend; docker-compose runs frontend+backend+MySQL locally. | Must | 2 | 2026-09-17
US-20 | Deployability - Azure (Section 11) | Developer | As a developer, I want the MVP deployed to Azure so it's accessible outside my machine. | Frontend and backend reachable over HTTPS on Azure; backend connects to managed DB; secrets via Azure config. | Must | 3 | 2026-09-17
US-21 | Finalization (Section 12) | Developer | As a developer, I want polished documentation and a demo-ready build so I can present SmartDesk confidently. | README, architecture/ER diagrams, and a working demo script are complete; deployment verified end-to-end. | Must | 2 | 2026-09-18

## Task Plan & Timeline
Date | Weekday | Sprint Focus (per SRS Sec. 12) | Daily Tasks | Deliverable / Exit Criteria | Related Stories
2026-09-02 | Wednesday | Project setup | Init Git repo; scaffold Spring Boot project; scaffold React project; create MySQL schema; set up initial architecture and environment configuration. | Repos created; base backend/frontend run locally; DB reachable.
2026-09-03 | Thursday | Authentication (part 1) | User entity + repository; registration endpoint; password hashing (BCrypt); Spring Security base config. | User can register via API with hashed password stored. | US-01
2026-09-04 | Friday | Authentication (part 2) | Login endpoint; JWT issuing/validation; role field on User; protected route middleware. | User can log in and receive a JWT; protected endpoint rejects missing/invalid token. | US-02, US-03
2026-09-07 | Monday | Core ticket system (part 1) | Ticket + Category entities and relationships; create-ticket endpoint; list-tickets endpoint scoped by role. | Employee can create and list tickets via API. | US-04
2026-09-08 | Tuesday | Core ticket system (part 2) | Ticket details endpoint; assign-ticket endpoint; update status/priority endpoint; resolve-ticket logic with resolved_at timestamp. | Agent can view, assign, update status/priority, and resolve a ticket via API. | US-06, US-07, US-08, US-10
2026-09-09 | Wednesday | Frontend MVP (part 1) | Login page; Register page; Auth context + protected routes; Employee Dashboard shell; Agent Dashboard shell. | User can log in through the UI and land on the correct dashboard. | US-02, US-05
2026-09-10 | Thursday | Frontend MVP (part 2) | Ticket list page; Create Ticket page; Ticket Details page (status/assignment/AI panel placeholders). | Employee can create/view tickets end-to-end in the UI. | US-04, US-05, US-06
2026-09-11 | Friday | Comments + validation | Comment entity + endpoints; comment UI on ticket details; Jakarta Validation on key DTOs; global exception handler; ticket filtering (status/category/priority). | Comments work end-to-end; invalid input returns consistent error responses; ticket list is filterable. | US-09
2026-09-14 | Monday | AI integration | Spring AI + OpenAI setup; ticket analysis service (category, priority, summary, suggested actions); graceful fallback if AI fails. | New tickets get AI-suggested category/priority/summary; agent can view and override it. | US-11, US-12
2026-09-15 | Tuesday | Dashboard + API documentation | Dashboard statistics endpoint (by status/category/priority, agent workload); React dashboard UI; Swagger/OpenAPI setup; minor UI refinement. | Dashboard shows live stats; all endpoints visible and testable in Swagger UI. | US-13, US-14, US-15, US-16, US-17
2026-09-16 | Wednesday | Testing | JUnit/Mockito tests for auth, ticket, and AI services; Postman collection; basic security/integration checks. | Core services covered by automated tests; Postman collection runs cleanly. | US-18
2026-09-17 | Thursday | Docker + Azure | Dockerfiles for backend/frontend; docker-compose for local dev; Azure hosting setup for frontend/backend; managed DB; env/secrets via Azure config; enable HTTPS. | docker-compose up runs the stack locally; app is reachable and functional on Azure over HTTPS. | US-19, US-20
2026-09-18 | Friday | Finalization | Bug fixes; README; architecture and ER diagrams; demo script and screenshots; final deployment verification (frontend↔backend↔DB on Azure). | Repo and live demo are presentation-ready. | US-21